## FINAL Runsheet_BCs v BAN 2nd OD
TIME | TIME OFFSET (hr.min) | ACTIVITY | LOCATION | PERSON RESPONSIBLE | NOTES | COMPLETED
MATCH DAY-2
15:00:00 |  | MD-2 Operations Meeting | Venue | All
MATCH DAY-1
09:00:00 |  | Bangladesh catering 1 | Venue | Caterers
10:00:00 |  | Bangladesh training begins | Venue | MA Ops Manager
10:30:00 |  | Bangladesh catering 2 | Venue | Caterers
13:00:00 |  | Bangladesh catering 3 | Venue | Caterers
13:00:00 |  | Bangladesh training ends | Venue | MA Ops Manager
13:00:00 |  | BLACKCAPS catering 1 | Venue | Caterers
13:15:00 |  | MD-1 Security Meeting | Venue | NZC Event Director
14:00:00 |  | BLACKCAPS training begins | Venue | MA Ops Manager
14:30:00 |  | MD-1 Match Officials Meeting | Venue | NZC Event Director
15:00:00 |  | H & S venue walkthrough | Venue | NZC Events Team | TBC timing between venue and NZC
15:15:00 |  | BLACKCAPS catering 2 | Venue | Caterers
17:00:00 |  | BLACKCAPS training ends | Venue | MA Ops Manager
MATCH DAY
10:00:00 | -04:00:00 | Drinks available for NZC Events | Event Presentation | Caterers
10:30:00 | -03:30:00 | NZC Events Onsite | Venue | NZC Events Team
11:00:00 | -03:00:00 | Visual walk around of venue noting health and safety issues | Venue | NZC Events Team
11:15:00 | -02:45:00 | Match Manager visual inspection of sightscreens, scoreboard operational, clock visible (either on scoreboard or manual) | Venue | Match Manager
11:30:00 | -01:15:00 | Ticket Box opens | Gates | Ticketek
11:40:00 | -02:20:00 | Bangladesh first group - estimated arrival time | PMOA | Match Manager
11:40:00 | -02:20:00 | PMOA Activated - estimated time | PMOA | ACU Manager | Activated on first team member arrival
12:00:00 | -02:00:00 | Bangladesh second group - estimated arrival time; 4th umpire - estimated arrival time | PMOA | Match Manager
12:00:00 | -02:00:00 | Team, MOs and NZC events catering ready | Venue | Caterers
12:00:00 | -02:00:00 | Match Officials Arrive | PMOA
12:00:00 | -02:00:00 | Event Production Briefing | Event Presentation | Event Pres Director | Incl Events team, Match Manager
12:00:00 | -02:00:00 | Venue Operations Centre (VOC) operational | Venue | NZC Event Director
12:15:00 | -01:45:00 | Team warm ups commence - estimate | Field of Play
12:25:00 | -01:35:00 | BLACKCAPS first group - estimated arrival time | PMOA | Match Manager
12:30:00 | -01:30:00 | Player and spectator ambulances in position on site | Venue | Medical
12:30:00 | -01:30:00 | Arrival snack available for scorers, media | Various | Caterers
12:30:00 | -01:30:00 | Public Gates open | Venue | All
12:40:00 | -01:20:00 | BLACKCAPS second group - estimated arrival time; rest of match officials - estimated arrival time | PMOA | Match Manager
12:45:00 | -01:15:00 | Match Day Doctor Arrives | Venue | Match Manager Medical
12:50:00 | -01:10:00 | Spark Sport wicketkeeping demo | Field of Play | Spark | On practice wicket if available
13:00:00 | -01:00:00 | Medical briefing | Field of Play | Match Manager Medical NZC Events Team | St John, Teams Physios, Match Day Doc, MO's
13:00:00 | -01:00:00 | All day beverage available for Match Referee | 3rd Umpire Box | Caterers
13:10:00 | -00:50:00 | Meet ANZ Coin Toss child | Gates | NZC Events Team
13:20:00 | -00:40:00 | Meet flagbearers at gates | Gates | NZC Events Team
13:20:00 | -00:40:00 | Jeff Crowe's 300th ODI as Match Referee presentation | Field of Play | Match Officials
13:30:00 | -00:30:00 | Replay screen Pre-Match build up | Venue | Event Presentation Monstavision
13:30:00 | -00:30:00 | Take photos of team lists, photocopy and distribute | Field of Play | Match Manager NZC Events Team | Scorers, Teams, Spark, Media, Radio Sport, MO's, Event Pres - 30 copies
13:32:00 | -00:28:00 | Coin Toss | Field of Play | Match Referee | Team Captains & MO's (3) required
13:42:00 | -00:18:00 | Spark Pitch Report | Field of Play | Spark
13:53:00 | -00:07:00 | Flag Bearers in postition | Field of Play | NZC Events Team
13:56:00 | -00:04:00 | Teams and match officials intro | Field of Play | Event Presentation
13:57:00 | -00:03:00 | Umpires and teams to tunnel | Players Entrance | Match Manager
13:58:00 | -00:02:00 | Teams to field | Field of Play | Event Presentation
14:00:00 | 00:00:00 | MATCH START - First innings commences | Field of Play | All
15:00:00 | +01:00:00 | Powerade Drinks break | Field of Play | Match Manager NZC Events Director | Powerade Drinks cart on FOP
15:00:00 | +01:00:00 | Canterbury Crease to Crease | Field of Play | NZC Commercial Team NZC Events Team | TBC, will choose most appropriate drinks break to do this activation
16:00:00 | +02:00:00 | Powerade Drinks break | Field of Play | Match Manager NZC Events Director | Powerade Drinks cart on FOP
17:15:00 | +03:00:00 | Dinner available for teams, MOs, media, NZC Events, scorers | Various | Caterers
17:30:00 | +03:30:00 | Dinner - First innings concludes | Field of Play | All
17:30:00 | +03:30:00 | ANZ Kids Takeover begins | Field of Play | NZC Community Team | Pre-selected young cricketers playing cricket on sectioned off area of the field
17:31:00 | +03:31:00 | Confirm second session start time |  | Match Manager
17:35:00 | +03:35:00 | Duckworth Lewis distributed |  | Match Manager | Teams, Event Pres, Scorer, MO's, Spark
17:50:00 | +03:50:00 | ANZ Kids Takeover ends | Field of Play | NZC Community Team
17:58:00 | +03:58:00 | Call Teams to Field | Field of Play | Match Manager | Link with Spark
18:00:00 | +04:00:00 | Second innings commences | Field of Play | All
19:00:00 | +05:00:00 | Powerade Drinks break | Field of Play | Match Manager NZC Events Director | Powerade Drinks cart on FOP
20:00:00 | +06:00:00 | Powerade Drinks break | Field of Play | Match Manager NZC Events Director | Powerade Drinks cart on FOP
21:20:00 | +07:20:00 | Post match meal ready for teams, MOs | Various | Caterers
21:30:00 | +07:30:00 | Estimated MATCH FINISH | Field of Play | All | Possible 30 mins add.
21:30:00 | +07:35:00 | PMOA deactivated at end of final session | PMOA | ACU Manager
21:35:00 | +07:35:00 | ANZ Player of the Match, onfield interviews | Field of Play | NZC Commercial Team NZC Events Team | POTM - Champagne (NZ), Pounamu (Ban)
21:40:00 | +07:40:00 | Player signing session | Boundary | Team | TBC
21:45:00 | +07:45:00 | Match Day Doctor off site |  | Medical
21:45:00 | +07:45:00 | Post Match press conference | Press Conference area | NZC Media team | Old Umpires Pavilion
21:50:00 | +07:50:00 | VOC Team Hot Debrief | Venue | Venue Ops | 15 mins after close of play - Venue, Events, CricOps, Police, 1st Aid, Security
22:20:00 | +08:20:00 | Events Team hot debrief | Venue | NZC Events Director | 30 mins after close of play
22:35:00 | +08:35:00 | Teams and Match Officials depart venue | Venue | Team | Team discretion